## Summary
Bellville Connect — ROM Summary (All Phases)
Inputs
Blended hourly rate | 50
Contingency | 0.3
Phase | Base hours (used) | Hours incl. contingency | Cost (base) | Cost incl. contingency
Phase 3 (MVP) | 3470 | 4511 | 173500 | 225550
Phase 4 (Growth) | 2810 | 3653 | 140500 | 182650
Phase 5 (Scale) | 2980 | 3874 | 149000 | 193700
TOTAL | 9260 | 12038 | 463000 | 601900
Notes
• Phase 3 includes tenant‑ready foundations; full multi‑tenant delivery is estimated in Phase 5 (see ROM Notes).
• Values are ROM ranges; a short paid scoping sprint tightens requirements and reduces estimation variance (see ROM Notes).

## ROM Notes
ROM Notes (Client-facing)
How to read this estimate | This spreadsheet provides a Rough Order of Magnitude (ROM) estimate by phase. ROMs are intended to support go/no‑go decisions and budgeting; they are not a fixed delivery quote.
What is included | Each phase lists client‑friendly work packages with a low/high hour range. The 'Hours used' column is an editable selection (default midpoint). Costs are calculated from your blended hourly rate.
Tenant readiness (important) | Phase 3 includes tenant‑ready foundations (tenant-aware data model and access scoping) to avoid expensive rework later. Full multi‑tenant SaaS capabilities (tenant provisioning, per‑tenant billing, white‑labeling) are estimated in Phase 5.
Why there is contingency | ROM contingency is a standard buffer for specification gaps and dependency risk (e.g., integration approvals, content readiness, AI approach). This is reduced after a short scoping sprint.
Key items to confirm in the paid scoping sprint (improves certainty) | 1) User roles + permissions (public, SMME, admin, moderator) 2) Verification workflow (what evidence, who reviews, SLAs) 3) Content operations (who creates/updates shelves/resources/events) 4) Integrations required in Phase 3 (WhatsApp, payments, maps, email) 5) AI approach for Phase 3 (assistive discovery vs automation) and provider flexibility requirement 6) Analytics/data foundations (events tracked from day 1, reporting needs) 7) Deployment posture + support expectations (hosting, uptime, backup)
Commercial framing (client-friendly) | We recommend: (a) ROM for budget alignment, followed by (b) a short paid scoping sprint to convert the roadmap into an implementation plan with clear acceptance criteria, timelines and a tighter estimate. Scoping can be credited against build if the project proceeds (optional).

## Phase 3 (MVP)
Bellville Connect — ROM Estimate (Phase 3 (MVP))
Purpose: Provide a Rough Order of Magnitude (ROM) estimate BEFORE paid scoping. Values are ranges and are only valid under stated assumptions.
Inputs (client-visible)
Blended hourly rate | 50 | Enter your blended rate (e.g., all-in average).
Contingency (risk buffer) | 30% | Applied to total hours to cover unknowns (typical ROM: 20%–50%).
Estimate scope | Phase 3 (MVP) + tenant-ready foundations (not full SaaS).
Work package (client-friendly) | What’s included (high level) | Dependencies / notes | Confidence | ROM hours (Low) | ROM hours (High) | Hours used (pick) | Cost (auto)
Delivery & coordination | Project management, sprint planning, stakeholder comms, demos, retrospectives. |  | Med | 140 | 240 | 190 | 9500
UX/UI (mobile-first) | Refine IA, key screens, accessibility, responsive behavior; iterate with pilot cohort. |  | Med | 160 | 280 | 220 | 11000
Platform foundations | Environments, auth, role-based access control, audit logs, tenant-ready scaffolding (tenant_id & scoping). |  | Low | 240 | 420 | 330 | 16500
Data model & persistence | Core entities: businesses, categories/tags, reviews, verification signals, resources, events; migrations. |  | Low | 220 | 380 | 300 | 15000
Directory & discovery | Business profile CRUD, search/browse, filters, basic map/location; featured/curated placements. |  | Med | 220 | 420 | 320 | 16000
Trust layer (verification + reviews) | Verification artifacts intake + admin review, staged signals/badges, reviews + moderation basics. |  | Low | 260 | 520 | 390 | 19500
Content system (shelves/curation) | Resources hub, events/opportunities, curated collections/shelves + simple admin publishing. |  | Low | 240 | 520 | 380 | 19000
WhatsApp integration (baseline) | Templates/flows, opt-in, reminders, basic automations (non-critical path). |  | Med | 120 | 260 | 190 | 9500
Payments & entitlements | Onboarding fee + subscription hooks, entitlements for premium placement (no full billing automation). |  | Low | 140 | 320 | 230 | 11500
AI assist (provider-agnostic) | Assistive Matchmaker + Mentor (RAG) over directory/resources; provider abstraction + eval loop. |  | Low | 260 | 560 | 410 | 20500
Analytics foundation (data product ready) | Event tracking plan + instrumentation, basic reporting exports, privacy/anonymization posture. |  | Med | 120 | 260 | 190 | 9500
QA, hardening & release | Test plan, regression, performance pass, security basics, release/rollback plan. |  | Med | 220 | 420 | 320 | 16000
Totals |  |  | Base hours | 2340 | 4600 | 3470 | 173500
|  |  | Hours incl. contingency |  |  | 4511 | 225550
Assumptions (ROM validity)
• Scope is Phase 3 (MVP) only. Items outside Phase 3 (MVP) are excluded unless explicitly listed.
• AI is assistive navigation/discovery (AI-assisted retrieval over the directory/resources), not autonomous agents or complex workflow automation.
• WhatsApp provider setup and message template approvals are outside the team’s direct control; schedule risk remains.
• Client provides timely content, taxonomy input, verification rules, and policy decisions (reviews/moderation) during build.
• Data volumes are moderate (beta cohort first); extreme scale hardening is out of scope for ROM.
Exclusions (can be scoped later)
• Phase 4 public launch enhancements (advanced promos, partner portals, full GTP dashboards) unless explicitly added.
• Phase 5 multi-tenant commercial SaaS features (tenant onboarding automation, billing per-tenant, white-label theming, tenant isolation hardening).
• Full ERP-style business tooling, deep integrations to external ERPs/CRMs, or advanced AI automation.
• Comprehensive legal review, POPIA/terms drafting (support provided but legal signoff external).

## Phase 4 (Growth)
Bellville Connect — ROM Estimate (Phase 4 (Growth))
Purpose: Provide a Rough Order of Magnitude (ROM) estimate BEFORE paid scoping. Values are ranges and are only valid under stated assumptions.
Inputs (client-visible)
Blended hourly rate | 50 | Enter your blended rate (e.g., all-in average).
Contingency (risk buffer) | 30% | Applied to total hours to cover unknowns (typical ROM: 20%–50%).
Estimate scope | Phase 4 (Growth) — build on MVP: dashboards, monetization, partner pipelines, ops tooling.
Work package (client-friendly) | What’s included (high level) | Dependencies / notes | Confidence | ROM hours (Low) | ROM hours (High) | Hours used (pick) | Cost (auto)
Delivery & coordination | Phase planning, governance, partner comms, milestone reporting, change control. |  | Med | 120 | 220 | 170 | 8500
UX/UI expansion | Deepen flows, reduce friction, improve content discovery, refine shelves/ranking UX. |  | Med | 160 | 300 | 230 | 11500
Dashboards & analytics (GTP) | GTP dashboards, KPI definitions, analytics layer implementation + reporting views. |  | Low | 240 | 520 | 380 | 19000
Monetization expansion | Premium promos, subscription billing completion, invoicing/receipts, entitlement management. |  | Low | 220 | 480 | 350 | 17500
Partnership content pipelines | Partner content ingestion, approvals, attribution, freshness workflows, moderation policy. |  | Med | 160 | 360 | 260 | 13000
AI automation upgrades | Guided workflows, smarter recommendations, feedback loops; maintain provider-agnostic layer. |  | Low | 220 | 520 | 370 | 18500
Operational tooling | Admin console upgrades, moderation queues, verification SLA tooling, audit/reporting. |  | Med | 200 | 420 | 310 | 15500
Performance & reliability | Caching, search tuning, observability/alerts, cost controls, backups/DR refinement. |  | Med | 180 | 380 | 280 | 14000
Security & compliance | POPIA/GDPR-aligned controls, retention policies, access reviews, threat model basics. |  | Med | 120 | 260 | 190 | 9500
QA & rollout | Expanded test suites, UAT cycles, pilot-to-broader rollout support. |  | Med | 180 | 360 | 270 | 13500
Totals |  |  | Base hours | 1800 | 3820 | 2810 | 140500
|  |  | Hours incl. contingency |  |  | 3653 | 182650
Assumptions (ROM validity)
• Scope is Phase 4 (Growth) only. Items outside Phase 4 (Growth) are excluded unless explicitly listed.
• AI is assistive navigation/discovery (RAG), not autonomous agents or complex workflow automation.
• WhatsApp provider setup and message template approvals are outside the team’s direct control; schedule risk remains.
• Client provides timely content, taxonomy input, verification rules, and policy decisions (reviews/moderation) during build.
• Data volumes are moderate (beta cohort first); extreme scale hardening is out of scope for ROM.
Exclusions (can be scoped later)
• Phase 4 public launch enhancements (advanced promos, partner portals, full GTP dashboards) unless explicitly added.
• Phase 5 multi-tenant commercial SaaS features (tenant onboarding automation, billing per-tenant, white-label theming, tenant isolation hardening).
• Full ERP-style business tooling, deep integrations to external ERPs/CRMs, or advanced AI automation.
• Comprehensive legal review, POPIA/terms drafting (support provided but legal signoff external).

## Phase 5 (Scale)
Bellville Connect — ROM Estimate (Phase 5 (Scale))
Purpose: Provide a Rough Order of Magnitude (ROM) estimate BEFORE paid scoping. Values are ranges and are only valid under stated assumptions.
Inputs (client-visible)
Blended hourly rate | 50 | Enter your blended rate (e.g., all-in average).
Contingency (risk buffer) | 30% | Applied to total hours to cover unknowns (typical ROM: 20%–50%).
Estimate scope | Phase 5 (Scale) — multi-tenant SaaS readiness + replicability + scale hardening.
Work package (client-friendly) | What’s included (high level) | Dependencies / notes | Confidence | ROM hours (Low) | ROM hours (High) | Hours used (pick) | Cost (auto)
Multi-tenant architecture (full) | Tenant provisioning, isolation strategy, tenant-scoped RBAC, per-tenant config. |  | Low | 320 | 720 | 520 | 26000
White-label / replicability | Branding/theming, content presets, tenant deployment automation, docs/playbooks. |  | Med | 240 | 560 | 400 | 20000
Per-tenant billing & plans | Tenant billing, invoicing, plan enforcement, metering hooks (if required). |  | Med | 220 | 520 | 370 | 18500
Scale & reliability hardening | Load/perf testing, horizontal scaling, multi-region options, resilience improvements. |  | Med | 240 | 560 | 400 | 20000
Advanced analytics & data products | Benchmarking, anonymized insights products, export APIs, report generation pipeline. |  | Med | 220 | 520 | 370 | 18500
AI capability expansion | More agents/assistants, evaluation harness, safety/guardrails, cost optimizations. |  | Med | 200 | 520 | 360 | 18000
Governance & operations | Support tooling, incident playbooks, admin delegation, audit/compliance reporting. |  | Med | 160 | 360 | 260 | 13000
QA & release engineering | CI/CD refinement, release trains, regression automation, staging environments per tenant. |  | Med | 180 | 420 | 300 | 15000
Totals |  |  | Base hours | 1780 | 4180 | 2980 | 149000
|  |  | Hours incl. contingency |  |  | 3874 | 193700
Assumptions (ROM validity)
• Scope is Phase 5 (Scale) only. Items outside Phase 5 (Scale) are excluded unless explicitly listed.
• AI is assistive navigation/discovery (RAG), not autonomous agents or complex workflow automation.
• WhatsApp provider setup and message template approvals are outside the team’s direct control; schedule risk remains.
• Client provides timely content, taxonomy input, verification rules, and policy decisions (reviews/moderation) during build.
• Data volumes are moderate (beta cohort first); extreme scale hardening is out of scope for ROM.
Exclusions (can be scoped later)
• Phase 4 public launch enhancements (advanced promos, partner portals, full GTP dashboards) unless explicitly added.
• Phase 5 multi-tenant commercial SaaS features (tenant onboarding automation, billing per-tenant, white-label theming, tenant isolation hardening).
• Full ERP-style business tooling, deep integrations to external ERPs/CRMs, or advanced AI automation.
• Comprehensive legal review, POPIA/terms drafting (support provided but legal signoff external).